## LOP
Z121 Bodyshop - Open Issues Tracking | [11 empty] | CLOSED | 2
[12 empty] | WIP | 2
[12 empty] | OPEN | 2
[12 empty] | Total | 6
No. | Priority | Line (Zone) | Stn.No | Raised By | Organization | Responsibility | Issue start Date | Concern / Question | Image (if required ) | Target Date (Due Date) | Countermeasure / Answer | Closing Date | Status (Open/Close & WIP) | Remarks (Final-Response)
1 |  |  |  | Mahantesh N | Mahindra | Kiran A | 2025-07-30 | Project Kick Off Meeting |  | 2025-07-30 |  | 2025-07-30 | Close | Project Kick off Meeting with M&M Team carried out
2 |  |  |  | Mahantesh N | Mahindra | Kiran A | 2025-07-30 | TKAB Project Organizational Structure |  | 2025-07-30 |  | 2025-07-30 | Close | Project Execution Team Introudction given to M&M Team
3 |  |  |  | Sumit B | TKAB | Mahantesh N | 2025-07-30 | Purchase Order |  | 2025-08-11 |  |  | WIP | Mahindra needs to share PO with TKAB
8 |  |  |  | Sumit B | TKAB | Mahantesh N |  | Robot Make Fanuc / Kuka
4 |  |  |  | Sumit B | TKAB | Mahantesh N | 2025-07-31 | Input Data Requirement as per checklist shared by TKAB for Design and Simulation |  | 2025-08-07 |  |  | WIP | Product Data and Simulation Cell data shared by M&M, Rest of the data as per checklist is pending
5 |  |  |  | Prathamesh T | TKAB | Prashant T | 2025-08-01 | Controls BOM Approval for ordering |  | 2025-08-07 |  |  | Open | Mahindra to give an approval on Controls BOM shared by TKAB for ordering
6 |  |  |  | Yashodhan J | TKAB | Shubham S | 2025-08-04 | Lifter Stroke and Cycle time Consideration |  | 2025-08-08 |  |  | Open | Mahindra to confirm the variable lifter strokes of 600MM and 800MM along with the cycle time cosnidered
7 |  |  |  | Sumit B | TKAB | Mahantesh N |  | Feedback on query list shared by tkAB design team
9
10
11
12 | [13 empty] | s
13
14
15
16
17
18
19
20
22
21
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
88

## M Z121 Schedule
SIGNIFICANCE
MAKER - thyssenkrupp Automotive Body Solutions Private Limited |  |  |  | Project Start: | 2025-07-29 |  |  |  | PLAN |  |  |  |  | DELAY
PROJECT -Z121 |  |  |  | Today: | 2025-08-13 |  |  |  | ACTUAL |  |  |  |  | CURRENT
PM - SUMIT BABEL |  |  |  | Display Week: | 1 |  |  |  | 2025-07-29 | [6 empty] | 2025-08-05 | [6 empty] | 2025-08-12 | [6 empty] | 2025-08-19 | [6 empty] | 2025-08-26 | [6 empty] | 2025-09-02 | [6 empty] | 2025-09-09 | [6 empty] | 2025-09-16 | [6 empty] | 2025-09-23 | [6 empty] | 2025-09-30 | [6 empty] | 2025-10-07 | [6 empty] | 2025-10-14 | [6 empty] | 2025-10-21 | [6 empty] | 2025-10-28 | [6 empty] | 2025-11-04 | [6 empty] | 2025-11-11 | [6 empty] | 2025-11-18 | [6 empty] | 2025-11-25 | [6 empty] | 2025-12-02 | [6 empty] | 2025-12-09 | [6 empty] | 2025-12-16 | [6 empty] | 2025-12-23 | [6 empty] | 2025-12-30 | [6 empty] | 2026-01-06 | [6 empty] | 2026-01-13 | [6 empty] | 2026-01-20 | [6 empty] | 2026-01-27 | [6 empty] | 2026-02-03 | [6 empty] | 2026-02-10 | [6 empty] | 2026-02-17 | [6 empty] | 2026-02-24 | [6 empty] | 2026-03-03 | [6 empty] | 2026-03-10 | [6 empty] | 2026-03-17 | [6 empty] | 2026-03-24 | [6 empty] | 2026-03-31 | [6 empty] | 2026-04-07 | [6 empty] | 2026-04-14 | [6 empty] | 2026-04-21 | [6 empty] | 2026-04-28 | [6 empty] | 2026-05-05 | [6 empty] | 2026-05-12 | [6 empty] | 2026-05-19 | [6 empty] | 2026-05-26 | [6 empty] | 2026-06-02 | [6 empty] | 2026-06-09 | [6 empty] | 2026-06-16 | [6 empty] | 2026-06-23
[9 empty] | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21
Sr.No. |  | ACTIVITY | RESPONSIBLE | PROGRESS | START | END | ACTUAL VS PLAN | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Weld Line Design, DAP & 2D Release | 1.1 | PO /LOI | Mahindra | 100% | 2025-07-28 | 2025-08-04 | PLAN | DAYS: 8
|  |  |  | 50% | 2025-07-28 |  | ACTUAL
| 1.2 | Project Kick-Off Meeting with Customer | Mahindra / tkAB | 0% | 2025-07-30 | 2025-07-30 | PLAN | bar: DAYS
|  |  |  | 100% | 2025-07-30 | 2025-07-30 | ACTUAL | bar: DAYS
| 1.3 | Product data & document sharing | Mahindra | 100% | 2025-07-31 | 2025-08-04 | PLAN | DAYS: 5
|  |  |  | 20% | 2025-08-04 |  | ACTUAL
| 1.4 | Process Validation | tkAB | 0% | 2025-08-01 | 2025-08-26 | PLAN | DAYS: 26
|  |  |  | 0% |  |  | ACTUAL
| 1.7 | Process Review | Mahindra / tkAB | 0% | 2025-08-26 | 2025-08-29 | PLAN | DAYS: 4
|  |  |  | 0% |  |  | ACTUAL
| 1.6 | Concept 3D design | tkAB | 0% | 2025-08-11 | 2025-09-10 | PLAN | DAYS: 31
|  |  |  | 0% |  |  | ACTUAL
| 1.7 | Concept Design Review with Mahindra | Mahindra / tkAB | 0% | 2025-09-08 | 2025-09-12 | PLAN | DAYS: 5
|  |  |  | 0% |  |  | ACTUAL
| 1.8 | Long Lead BOM preparation & approval from Mahindra | Mahindra / tkAB | 0% | 2025-08-11 | 2025-09-20 | PLAN | DAYS: 41
|  |  |  | 0% |  |  | ACTUAL
| 1.9 | PO for long lead items | tkAB | 0% | 2025-09-01 | 2025-09-27 | PLAN | DAYS: 27
|  |  |  | 0% |  |  | ACTUAL
| 1.10 | 3D Design | tkAB | 0% | 2025-09-12 | 2025-10-10 | PLAN | DAYS: 29
|  |  |  | 0% |  |  | ACTUAL
| 1.11 | FINAL _ DAP | Mahindra / tkAB | 0% | 2025-10-13 | 2025-10-17 | PLAN | DAYS: 5
|  |  |  | 0% |  |  | ACTUAL
| 1.12 | Design updation ,Detailing & Final Release | tkAB | 0% | 2025-10-20 | 2025-11-17 | PLAN | DAYS: 29
|  |  |  | 0% |  |  | ACTUAL
| 1.13 | Electrical Design | tkAB | 0% | 2025-10-13 | 2025-11-27 | PLAN | DAYS: 46
|  |  |  | 0% |  |  | ACTUAL
| 1.14 | Offline programming (PLC) | tkAB | 0% | 2025-11-24 | 2026-01-13 | PLAN | DAYS: 51
|  |  |  | 0% |  |  | ACTUAL
| 1.15 | FINAL _ Electrical Design Review E -DAP & corrections | Mahindra / tkAB | 0% | 2025-12-01 | 2025-12-05 | PLAN | DAYS: 5
|  |  |  | 0% |  |  | ACTUAL
Simulation, OLP & VC | 2.1 | Robot simulation Concept | tkAB | 0% | 2025-09-15 | 2025-10-30 | PLAN | DAYS: 46
|  |  |  | 0% |  |  | ACTUAL
| 2.2 | Detailed Simulation | tkAB | 0% | 2025-10-30 | 2025-11-14 | PLAN | DAYS: 16
|  |  |  | 0% |  |  | ACTUAL
| 2.3 | FINAL _ Simulation Approval ( SAP ) | Mahindra / tkAB | 0% | 2025-11-10 | 2025-11-17 | PLAN | DAYS: 8
|  |  |  | 0% |  |  | ACTUAL
| 2.4 | OLP Preparation | tkAB | 0% | 2025-11-18 | 2026-01-07 | PLAN | DAYS: 51
|  |  |  | 0% |  |  | ACTUAL
| 2.4 | OLP Submit | tkAB | 0% | 2026-01-05 | 2026-01-15 | PLAN | DAYS: 11
|  |  |  | 0% |  |  | ACTUAL
| 2.5 | FINAL _ OLP Approval ( OLP B/O ) | Mahindra / tkAB | 0% | 2026-01-15 | 2026-01-19 | PLAN | DAYS: 5
|  |  |  | 0% |  |  | ACTUAL
| 2.6 | Final PLC& HMI program submission | tkAB | 0% | 2026-01-20 | 2026-02-09 | PLAN | DAYS: 21
|  |  |  | 0% |  |  | ACTUAL
| 2.7 | IO mapped VC ready Simulation cells | tkAB | 0% | 2026-02-09 | 2026-02-24 | PLAN | DAYS: 16
|  |  |  | 0% |  |  | ACTUAL
| 2.8 | Virtual Commissioning testing & validation | tkAB | 0% | 2026-02-25 | 2026-03-12 | PLAN | DAYS: 16
|  |  |  | 0% |  |  | ACTUAL
| 2.8 | FINAL _ Virtual Commissioning Buy-off | Mahindra / tkAB | 0% | 2026-03-13 | 2026-03-28 | PLAN | DAYS: 16
|  |  |  | 0% |  |  | ACTUAL
Manufacturing, Assembly & Self certify | 3.1 | Manufacturing | tkAB | 0% | 2025-11-10 | 2026-01-09 | PLAN | DAYS: 61
|  |  |  | 0% |  |  | ACTUAL
| 3.2 | Long lead BO items receipt | tkAB | 0% | 2025-10-18 | 2026-02-15 | PLAN | DAYS: 121
|  |  |  | 0% |  |  | ACTUAL
| 3.12 | Mechanical & Electrical assembly of fixtures | tkAB | 0% | 2025-12-10 | 2026-01-15 | PLAN | DAYS: 37
|  |  |  | 0% |  |  | ACTUAL
| 3.13 | CMM Inhouse, Gap Setting & Part fitment | tkAB | 0% | 2026-01-06 | 2026-02-06 | PLAN | DAYS: 32
|  |  |  | 0% |  |  | ACTUAL
| 3.14 | IO check & electrical check | tkAB | 0% | 2026-01-27 | 2026-02-13 | PLAN | DAYS: 18
|  |  |  | 0% |  |  | ACTUAL
| 3.15 | Supplier self certification - M1, M2, Controls, Process & Electrical HW | tkAB | 0% | 2026-02-10 | 2026-02-18 | PLAN | DAYS: 9
|  |  |  | 0% |  |  | ACTUAL
Limited Trial, Buy-off & Dispatch | 4.1 | M&M Sample Check - Process, M1 & M2 | Mahindra / tkAB | 0% | 2026-02-10 | 2026-02-19 | PLAN | DAYS: 10
|  |  |  | 0% |  |  | ACTUAL
| 4.2 | M&M Sample Check - Electrical HW & Controls | Mahindra / tkAB | 0% | 2026-02-17 | 2026-02-19 | PLAN | DAYS: 3
|  |  |  | 0% |  |  | ACTUAL
| 4.3 | Open points closing | tkAB | 0% | 2026-02-19 | 2026-02-22 | PLAN | DAYS: 4
|  |  |  | 0% |  |  | ACTUAL
| 4.4 | FINAL _ Buy-off | Mahindra / tkAB | 0% | 2026-02-19 | 2026-02-26 | PLAN | DAYS: 8
|  |  |  | 0% |  |  | ACTUAL
| 4.5 | Dismantling & Packing | tkAB | 0% | 2026-02-21 | 2026-03-05 | PLAN | DAYS: 13
|  |  |  | 0% |  |  | ACTUAL
| 4.6 | Shipping & Receipt @ Chakan | tkAB | 0% | 2026-02-22 | 2026-03-06 | PLAN | DAYS: 13
|  |  |  | 0% |  |  | ACTUAL
Onsite | 5 | Line Installation | tkAB | 0% | 2026-03-02 | 2026-04-21 | PLAN | DAYS: 51
|  |  |  | 0% |  |  | ACTUAL
| 6 | Commissioning & Trial Build | tkAB | 0% | 2026-03-22 | 2026-04-21 | PLAN | DAYS: 31
|  |  |  | 0% |  |  | ACTUAL
| 7 | TTO | Mahindra | 0% | 2026-04-22 | 2026-05-31 | PLAN | DAYS: 40
|  |  |  | 0% |  |  | ACTUAL
| 8 | Ready for VP Build | Mahindra / tkAB | 0% | 2026-06-01 |  | PLAN
|  |  |  | 0% |  |  | ACTUAL
Note on J6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.
Note on C7: Babel, Sumit: PO is yet to be received

## Procurement Plan
PROCUREMENT PLAN MAHINDRA Z121
| Sno | Item | Mahindra _ Approval Details | P1 CAB | P2 CARGO | P3 CLOSURES | TOTAL | Make | Release required from | Resp. Buyer | Expected Release from Design | Released Status | RFQ Release from PSM | Target PO date to supplier | PO release to supplier | PO No. | Min. STD Lead time in Weeks | Delivery Date required @ tkAB | Delivery date as per order acceptance | Delay in Days | REMARKS
| 1 | SEW Drives for Framer/Trunion/Turn Table |  | 16 | 9 | 7 | 32 | SEW | Prathamesh | Suyog C. | 2025-09-16 |  | 2025-09-21 |  | 2025-09-26 |  | 18 | 2026-01-30
| 2 | SEW motor for Framer |  | 4 | 6 | 0 | 10 | SEW | Prathamesh | Suyog C. | 2025-09-16 |  | 2025-09-21 |  | 2025-09-26 |  | 18 | 2026-01-30
| 3 | SEW motor for Trunion |  | 2 | 2 | 0 | 4 | SEW | Prathamesh | Suyog C. | 2025-09-16 |  | 2025-09-21 |  | 2025-09-26 |  | 18 | 2026-01-30
| 4 | SEW motor for Turn Table |  | 2 | 0 | 7 | 9 | SEW | Prathamesh | Suyog C. | 2025-09-16 |  | 2025-09-21 |  | 2025-09-26 |  | 18 | 2026-01-30
| 5 | Turn Table |  | 2 | 0 | 7 | 9 | Goizper | Vilas | Nilesh.G | 2025-09-07 |  | 2025-09-12 |  | 2025-09-17 |  | 12 | 2025-12-10
| 6 | Trunion |  | 2 | 2 | 0 | 4 | Goizper | Vilas | Nilesh.G | 2025-09-08 |  | 2025-09-13 |  | 2025-09-18 |  | 12 | 2025-12-11
| 7 | Encoder Cables for Framer/Trunion/Turn table |  | 12 | 9 | 7 | 32 | SEW | Prathamesh | Suyog C. | 2025-09-16 |  | 2025-09-21 |  | 2025-09-26 |  | 18 | 2026-01-30
| 8 | ROCKWELL Drives for Conveyor ( PRB) |  | 33 | 3 | 0 | 36 | AB | Prathamesh | Narayan M. | 2025-09-30 |  | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 9 | Power Cylinders (Clamp/Guide./Compact) & Fittings : Lot 1 |  | 1247 | 761 | 390 | 2398 | DESTACO | Vilas | Suyog C. | 2025-09-02 |  | 2025-09-07 |  | 2025-09-12 |  | 12 | 2025-12-05
| 10 | Brake Cylinder |  |  |  |  | 112 | CKD | Vilas | Nilesh.G | 2025-09-02 |  | 2025-09-07 |  | 2025-09-12 |  | 12 | 2025-12-05
| 11 | Roller bed with lifter | 8 | 9 | 0 | 0 | 9 | TUNKERS | Vilas | Nilesh.G / Shekhar P | 2025-10-28 |  | 2025-11-02 |  | 2025-11-07 |  | 12 | 2026-01-30
| 12 | Roller bed without lifter | 7 | 13 | 0 | 0 | 13 | TUNKERS | Vilas | Nilesh.G / Shekhar P | 2025-10-28 |  | 2025-11-02 |  | 2025-11-07 |  | 12 | 2026-01-30
| 13 | Lifter Mechanism for roof bow |  |  |  |  | 1 | Irobotic/ fine handling | Vilas | Suyog C. | 2025-09-15 |  | 2025-09-20 |  | 2025-09-25 |  | 16 | 2026-01-15
| 14 | APC Conveyor |  | 4 | 0 | 0 | 4 | TUNKERS | Vilas | Nilesh.G / Shekhar P | 2025-10-28 |  | 2025-11-02 |  | 2025-11-07 |  | 12 | 2026-01-30
| 15 | APC Hanger |  |  |  |  | 33 | Manufacturing | Vilas | Shekhar.P | 2025-11-25 |  | 2025-11-30 |  | 2025-12-05 |  | 8 | 2026-01-30
| 16 | Suction Cup ,Holder & Vaccum Generator |  |  |  |  | 327 | Piab | Vilas | Nilesh.G | 2025-11-25 |  | 2025-11-30 |  | 2025-12-05 |  | 8 | 2026-01-30
| 18 | PLC Control Panel M-Panel (H 1800 x W2000 x D500), Mounting Stand(H 200 x W2000 x D500) |  | 5 | 1 | 2 | 8 | tkab | Prathamesh | Narayan M. | 2025-09-30 | RFQ submitted | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 19 | PLC Panel A-Panel (H 1800 x W2000 x D500), Mounting Stand(H 200 x W2000 x D500) |  | 0 | 1 | 0 | 1 | tkab | Prathamesh | Narayan M. | 2025-09-30 | RFQ submitted | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 20 | Servo Drive Panel Main Framer/Trunion/Turn Table (H 1800 x W2000 x D500), Mounting Stand(H 200 x W2000 x D500) |  | 4 | 2 | 4 | 10 | tkab | Prathamesh | Narayan M. | 2025-09-30 | RFQ submitted | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 21 | Safety Junction box (H 800 x W 800 x D210), |  | 25 | 10 | 7 | 42 | tkab | Prathamesh | Narayan M. | 2025-09-30 | RFQ submitted | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 22 | Manual Gun Junction box (H 200 x W 440 x D 180) |  | 13 | 3 | 3 | 19 | tkab | Prathamesh | Narayan M. | 2025-09-30 | RFQ submitted | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 23 | 24VDC JB (H 300 x W 300 x D120) |  | 97 | 24 | 20 | 141 | tkab | Prathamesh | Narayan M. | 2025-08-05 | RFQ submitted | 2025-08-10 |  | 2025-08-15 |  | 16 | 2025-12-05
| 24 | TurnTable JB (H 400 x W 500 x D120) |  | 3 | 3 | 8 | 14 | tkab | Prathamesh | Narayan M. | 2025-09-30 | RFQ submitted | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 25 | Takeout station Box (H 300 x W 120 x D xxx) |  | 5 | 2 | 1 | 8 | tkab | Prathamesh | Narayan M. | 2025-09-30 | RFQ submitted | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 26 | Gate Box (H 300 x W 300 x D 125), |  | 31 | 10 | 11 | 52 | tkab | Prathamesh | Narayan M. | 2025-09-30 | RFQ submitted | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 27 | Single phase PDP panel (H 1000 x W 800 x D 300) |  | 10 | 4 | 4 | 18 | tkab | Prathamesh | Narayan M. | 2025-09-30 | RFQ submitted | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 28 | Vin Punching |  | 1 | 1 | 0 | 2 | Gravotech | Vilas | Nilesh.G | 2025-10-28 |  | 2025-11-02 |  | 2025-11-07 |  | 12 | 2026-01-30
| 29 | Air and Preparation Unit |  | 32 | 24 | 12 | 68 | FESTO | Vilas | Narayan M. | 2025-10-10 |  | 2025-10-15 |  | 2025-10-20 |  | 8 | 2025-12-15
| 30 | WATER HEADER |  | 22 | 10 | 9 | 41 | SMC | Vilas | Narayan M. | 2025-09-17 |  | 2025-09-22 |  | 2025-09-27 |  | 12 | 2025-12-20
| 31 | WATER SAVER |  | 4 | 22 | 0 | 26 | SMC | Vilas | Narayan M. | 2025-09-17 |  | 2025-09-22 |  | 2025-09-27 |  | 12 | 2025-12-20
| 32 | Proxi Sensors |  | 418 | 290 | 152 | 860 | Contrinex | Vilas | Narayan M. | 2025-09-30 |  | 2025-10-05 |  | 2025-10-10 |  | 8 | 2025-12-05
| 34 | Valve Bank/Fittings/Pneumatic Tube |  | 75 | 44 | 28 | 147 | FESTO | Vilas | Narayan M. | 2025-09-30 |  | 2025-10-05 |  | 2025-10-10 |  | 8 | 2025-12-05
| 35 | HMI with stand |  | 36 | 10 | 8 | 54 | ROCKWELL | Vinay | Narayan M. | 2025-09-30 |  | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 36 | Roller Bearings |  |  |  |  | 0 | WINKEL | Vilas | Kiran R | 2025-08-12 |  | 2025-08-17 |  | 2025-08-22 |  | 15 | 2025-12-05
| 37 | Lubrication Fittings |  |  |  |  | 0 | PERMA-TEC | Vilas | Suyog C. | 2025-08-05 |  | 2025-08-10 |  | 2025-08-15 |  | 16 | 2025-12-05
| 38 | Strip Brushes |  |  |  |  | 0 | Mink Bürsten | Vilas | Suyog C. | 2025-08-05 |  | 2025-08-10 |  | 2025-08-15 |  | 16 | 2025-12-05
| 39 | Drive Shafts |  |  |  |  | 0 | Elbe | Vilas | Suyog C. | 2025-08-05 |  | 2025-08-10 |  | 2025-08-15 |  | 16 | 2025-12-05
| 40 | Drag Chains |  |  |  |  | 0 | Igus | Vilas | Nilesh.G | 2025-10-14 |  | 2025-10-19 |  | 2025-10-24 |  | 6 | 2025-12-05
| 41 | Pipe Clamps |  |  |  |  | 0 | Stauff | Vilas | Nilesh.G | 2025-10-01 |  | 2025-10-06 |  | 2025-10-11 |  | 8 | 2025-12-06
| 42 | Roller Limt Switches |  |  |  |  | 0 | Schmersal | Vilas | Narayan M. | 2025-10-24 |  | 2025-10-29 |  | 2025-11-03 |  | 6 | 2025-12-15
| 43 | Oilless Bushes |  |  |  |  | 0 | Sankyo | Vilas | Nilesh.G | 2025-10-24 |  | 2025-10-29 |  | 2025-11-03 |  | 6 | 2025-12-15
| 45 | ATC Robot side |  | 19 | 15 | 2 | 36 | WALTHER | Rohit | Vikram.W | 2025-09-30 |  | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 46 | ATC Tool side |  | 43 | 32 | 4 | 79 | WALTHER | Rohit | Vikram.W | 2025-09-30 |  | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 47 | Weld Guns |  | 37 | 32 | 9 | 78 | OBARA | Rohit | Suyog C. | 2025-09-30 |  | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 48 | Tip Dresser |  | 37 | 32 | 9 | 78 | OBARA | Rohit | Suyog C. | 2025-09-30 |  | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 49 | Robotic Sealant System |  | 3 | 0 | 1 | 4 | PATVIN | Vilas | Suyog C. | 2025-09-30 | RFQ submitted | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 50 | Vision for Robotic Sealant System |  | 3 | 0 | 1 | 4 | KEYENCE | Vilas | Narayan M. | 2025-09-30 |  | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 51 | Vision for Pick and Place |  | 0 | 1 | 0 | 1 | ISRA | Vilas | Suyog C. | 2025-09-02 |  | 2025-09-07 |  | 2025-09-12 |  | 20 | 2026-01-30
| 52 | Robotic Stud |  | 0 | 2 | 0 | 2 | Tucker | Rohit | Suyog C. | 2025-09-30 |  | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 53 | Ethernet Cables |  | 470 | 300 | 155 | 925 | MURR | Vinay | Narayan M. | 2025-09-30 |  | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 54 | GateSwitch |  | 31 | 10 | 11 | 52 | Euchner + Sick gate plug | Vinay | Narayan M. | 2025-09-30 |  | 2025-10-05 |  | 2025-10-10 |  | 16 | 2026-01-30
| 55 | Risers/Mylars/Clamp arms/Pins/Unit Assy parts | [5 empty] | Local | Vilas | Kiran R | 2025-10-17 |  | 2025-10-22 |  | 2025-10-27 |  | 5 | 2025-12-01
| 56 | Mechanical BOC (Bush/ Magnets) |  |  |  |  | 0 | Misumi | Vilas | Narayan M. | 2025-10-24 |  | 2025-10-29 |  | 2025-11-03 |  | 4 | 2025-12-01
| 57 | Hardware items |  |  |  |  | 0 | Unbrako | Vilas | Vikram.W | 2025-10-23 |  | 2025-10-28 |  | 2025-11-02 |  | 4 | 2025-11-30
| 58 | Fixture Base |  | 47 | 17 | 22 | 86 | LOCAL | Vilas | Shekhar.P | 2025-10-09 |  | 2025-10-14 |  | 2025-10-19 |  | 6 | 2025-11-30
| 59 | Fixture cable trays |  |  |  |  | 0 | Manufacturing | Vilas | Nilesh.G | 2025-10-14 |  | 2025-10-19 |  | 2025-10-24 |  | 6 | 2025-12-05
| 60 | Hemming Beds |  | 0 | 0 | 5 | 5 | Manufacturing | Vilas | Shekhar.P | 2025-09-03 |  | 2025-09-08 |  | 2025-09-13 |  | 14 | 2025-12-20
| 61 | Roller Head for Hemming |  | 0 | 0 | 5 | 5 | Tkab | Rohit | Nilesh.G | 2025-09-16 |  | 2025-09-21 |  | 2025-09-26 |  | 18 | 2026-01-30
| 62 | Fabricated Grippers |  | 14 | 15 | 7 | 36 | LOCAL | Vilas | Shekhar.P | 2025-10-14 |  | 2025-10-19 |  | 2025-10-24 |  | 6 | 2025-12-05
| 63 | EGT grippers |  | 3 | 3 |  | 6 | TUNKER/FEE | Vilas | Nilesh.G | 2025-08-23 |  | 2025-08-28 |  | 2025-09-02 |  | 12 | 2025-11-25
| 64 | Panel Wiring Cables |  |  |  |  | 0 | Lapp | Vinay | Narayan M. | 2025-08-27 |  | 2025-09-01 |  | 2025-09-06 |  | 8 | 2025-11-01
| 65 | Light Curtains |  | 50 | 20 | 8 | 78 | SICK | Vilas | Narayan M. | 2025-10-28 |  | 2025-11-02 |  | 2025-11-07 |  | 12 | 2026-01-30
| 66 | Safety Mats |  | 36 | 30 | 6 | 72 | AB | Vilas | Narayan M. | 2025-10-28 |  | 2025-11-02 |  | 2025-11-07 |  | 12 | 2026-01-30
| 67 | Field Wiring Cables |  | 325 | 175 | 180 | 680 | Lapp | Vinay | Narayan M. | 2025-10-28 |  | 2025-11-02 |  | 2025-11-07 |  | 12 | 2026-01-30
| 68 | Limit Switches |  |  |  |  | 0 | Omron | Vilas | Narayan M. | 2025-09-12 |  | 2025-09-17 |  | 2025-09-22 |  | 12 | 2025-12-15
| 69 | Circuit Breakers |  |  |  |  | 0 | Siemens | Vinay | Narayan M. | 2025-11-25 |  | 2025-11-30 |  | 2025-12-05 |  | 8 | 2026-01-30
| 70 | Relays/Relay Base/Door Switch/SMPS/Short Bars |  |  |  |  | 0 | Omron | Vinay | Narayan M. | 2025-11-25 |  | 2025-11-30 |  | 2025-12-05 |  | 8 | 2026-01-30
| 71 | Fences |  | 402 | 230 | 195 | 827 | TROAX / INHOUSE | Vilas | Vikram.W | 2025-10-14 |  | 2025-10-19 |  | 2025-10-24 |  | 14 | 2026-01-30
| 72 | Sensor Cables |  |  |  |  | 0 | Murr | Vinay | Narayan M. | 2025-09-30 |  | 2025-10-05 |  | 2025-10-10 |  | 8 | 2025-12-05
| 73 | Tower Lamp |  | 141 | 21 | 32 | 194 | Banner | Vinay | Narayan M. | 2025-11-25 |  | 2025-11-30 |  | 2025-12-05 |  | 8 | 2026-01-30
| 74 | Push Buttons,Selctor Switch, E-stop,Lamps,Jumpers,End Plates,ILPB ,PB Box etc |  |  |  |  | 0 | Schneider Electric | Vinay | Narayan M. | 2025-11-25 |  | 2025-11-30 |  | 2025-12-05 |  | 8 | 2026-01-30
| 75 | Field Cable Trays |  | 705 | 290 | 273 | 1268 | LOCAL | Vinay | Nilesh.G | 2025-11-19 |  | 2025-11-24 |  | 2025-11-29 |  | 6 | 2026-01-10
| 76 | Utility |  | 900 | 576 | 322 | 1798 | LOCAL | Nitin Shinde | Suyog C. | 2025-12-09 |  | 2025-12-14 |  | 2025-12-19 |  | 6 | 2026-01-30
| 77 | Robot Pedestals |  | 24 | 24 | 11 | 59 | LOCAL | Vilas | Rahul S | 2025-12-09 |  | 2025-12-14 |  | 2025-12-19 |  | 6 | 2026-01-30
| 78 | Tip Dresser Stands |  | 30 | 26 | 9 | 65 | LOCAL | Vilas | Shekhar.P | 2025-12-23 |  | 2025-12-28 |  | 2026-01-02 |  | 4 | 2026-01-30
| 79 | Weld Timer Stands |  | 37 | 32 | 11 | 80 | LOCAL | Vilas | Shekhar.P | 2025-12-23 |  | 2025-12-28 |  | 2026-01-02 |  | 4 | 2026-01-30
| 80 | PLC Panel stands |  | 5 | 2 | 2 | 9 | LOCAL | Vilas | Shekhar.P | 2025-12-23 |  | 2025-12-28 |  | 2026-01-02 |  | 4 | 2026-01-30
| 81 | Bellows |  |  |  |  | 0 | Hema | Vilas | Suyog C. | 2025-11-25 |  | 2025-11-30 |  | 2025-12-05 |  | 4
| 82 | Cone Clamping |  |  |  |  | 0 | Ringspann | Vilas | Nilesh.G | 2025-10-14 |  | 2025-10-19 |  | 2025-10-24 |  | 6 | 2025-12-05
| 83 | Polyurethane Bumpers |  |  |  |  | 0 | Enidine | Vilas | Suyog C. | 2025-11-25 |  | 2025-11-30 |  | 2025-12-05 |  | 8
| 84 | In process trollies |  |  |  |  | 0 | Manufacturing | Vilas | Shekhar.P | 2025-11-25 |  | 2025-11-30 |  | 2025-12-05 |  | 8 | 2026-01-30
| 85 | Tackles |  | 30 | 10 | 16 | 56 | Manufacturing | Vilas | Shekhar.P | 2025-12-09 |  | 2025-12-14 |  | 2025-12-19 |  | 6 | 2026-01-30
| 86 | FRL |  | 71 | 39 | 28 | 138 | Festo/SMC | Vilas | Narayan M. | 2025-09-30 |  | 2025-10-05 |  | 2025-10-10 |  | 8 | 2025-12-05
| 87 | FRP Templates |  |  |  |  | 44 | Manufacturing | Vilas | Shekhar.P | 2025-12-09 |  | 2025-12-14 |  | 2025-12-19 |  | 6 | 2026-01-30
| 88 | Sealer Stand |  | 10 | 2 | 8 | 20 | Manufacturing | Vilas | Shekhar.P | 2025-12-09 |  | 2025-12-14 |  | 2025-12-19 |  | 6 | 2026-01-30
| 89 | Loading Table |  | 13 | 18 | 0 | 31 | Manufacturing | Vilas | Shekhar.P | 2025-10-14 |  | 2025-10-19 |  | 2025-10-24 |  | 6 | 2025-12-05
1 | 90 | Dresspack Installation (Service scope Only) |  | 26 | 24 | 0 | 50 | Becker |  | Nilesh.G | 2025-12-24 |  | 2025-12-29 |  | 2026-01-03 |  | 8 | 2026-02-28
| 91 | Trench Cover |  |  |  |  | 0 | Manufacturing | Vilas | Shekhar.P | 2025-12-23 |  | 2025-12-28 |  | 2026-01-02 |  | 4 | 2026-01-30
| 92 | Platform |  |  |  |  | 0 | Manufacturing | Vilas | Shekhar.P | 2025-11-25 |  | 2025-11-30 |  | 2025-12-05 |  | 8 | 2026-01-30
| 93 | Safety Guard |  |  |  |  | 0 | Manufacturing | Vilas | Shekhar.P | 2025-12-23 |  | 2025-12-28 |  | 2026-01-02 |  | 4 | 2026-01-30
| 94 | Operator Box |  | 84 | 18 | 16 | 118 | Fabricated | Prathamesh | Narayan M. | 2025-11-25 | RFQ submitted | 2025-11-30 |  | 2025-12-05 |  | 8 | 2026-01-30
| 95 | Water Hoses | [5 empty] | Yasung/Becker | Prathamesh | Narayan M. | 2025-11-25 |  | 2025-11-30 |  | 2025-12-05 |  | 8 | 2026-01-30
| 96 | Rolling Shutter |  |  |  |  | 2 | Avians/Nivha | Vilas | Suyog C. | 2025-10-28 |  | 2025-11-02 |  | 2025-11-07 |  | 12 | 2026-01-30
Formulas:
Expected Release from Design = [RFQ Release from PSM]-5
RFQ Release from PSM = [PO release to supplier]-5
PO release to supplier = +[Delivery Date required @ tkAB]-([Min. STD Lead time in Weeks]*7)
Note on S64: Author: required for panel built
Note on S69: Author: required for panel built
Note on S70: Author: required for panel built