## LOP (hidden)
Z121 Bodyshop - Open Issues Tracking | [11 empty] | CLOSED | 41
[12 empty] | WIP | 6
[12 empty] | OPEN | 4
[12 empty] | Total | 51
No. | Priority | Line (Zone) | Stn.No | Raised By | Organization | Responsibility | Issue start Date | Concern / Question | Image (if required ) | Target Date (Due Date) | Countermeasure / Answer | Closing Date | Status (Open/Close & WIP) | Remarks (Final-Response)
1 |  |  |  | Mahantesh N | Mahindra | Kiran A | 2025-07-30 | Project Kick Off Meeting |  | 2025-07-30 |  | 2025-07-30 | Close | Project Kick off Meeting with M&M Team carried out
2 |  |  |  | Mahantesh N | Mahindra | Kiran A | 2025-07-30 | TKAB Project Organizational Structure |  | 2025-07-30 |  | 2025-07-30 | Close | Project Execution Team Introudction given to M&M Team
3 |  |  |  | Sumit B | TKAB | Mahantesh N | 2025-07-30 | Purchase Order |  | 2025-08-11 |  | 2025-09-03 | Close | Mahindra needs to share PO with TKAB
8 |  |  |  | Sumit B | TKAB | Mahantesh N | 2025-07-30 | Robot Make Fanuc / Kuka |  | 2025-08-17 |  | 2025-08-22 | Close
4 |  |  |  | Sumit B | TKAB | Mahantesh N | 2025-07-31 | Input Data Requirement as per checklist shared by TKAB for Design and Simulation |  | 2025-08-07 |  | 2025-08-25 | Close | Product Data and Simulation Cell data shared by M&M, Rest of the data as per checklist is pending
7.2 |  |  |  | Prathamesh T | TKAB | Prashant T | 2025-08-01 | Controls BOM Approval for ordering |  | 07.08.2025 03-09-25 |  | 2025-09-09 | Close | Go ahead received from Mahindra controls team on 18.8.25 for ordering -The review of the PLC & Drive panel has been completed,
8.4 |  |  |  | Shripad R | TKAB | Mahantesh N | 2025-08-13 | Confirmation on PRB and EGT |  | 2025-08-14 |  | 2025-09-11 | Close | EGT approved for all grippers. PRB is approved as per presentation provided. Boughtouts confirmed. PRB pitch of 5.5m approved by M&M on 11-Sep.
9.6 |  |  |  | Deepak S | TKAB | Mahantesh N | 2025-08-18 | Robot Spec along with payload required |  | 2025-08-19 |  | 2025-08-22 | Close
10.8 |  |  |  | Sumit B | TKAB | Mahantesh N | 2025-08-21 | Fence make to be discussed & concluded |  | 2025-08-25 | Make to be concluded by Mahindra |  | Open
12 |  |  |  | Sumit B | TKAB | Prashant T | 2025-08-18 | Eplan Version, EPLAN P8_2023 software version, to be confirmed. |  | 2025-08-21 |  | 2025-08-21 | Close
13.2 |  |  |  | Rohit . Z | TKAB | Akhil /Shubham | 2025-08-21 | Need Clarification on NASH make guns used in which Robotic Lines |  | 2025-08-27 |  | 2025-09-04 | Close | Nash to be used in Bodysides.
14.4 |  |  |  | Vilas .V | TKAB | Mahantesh N | 2025-08-21 | Layout Queries Shared , mahindra to check & provide feedback | 2025-08-20 | 2025-08-26 |  | 2025-09-15 | Close | Additional column at the actual site, located between Grid M–N and H–I was obstructing. 1).The column between Grid H–I is interfering with the transfer system, just before the UB system- After review ot Mahindra and TKAB Team confirmed that there is no interferance 2).The column between Grid M–N is obstructing the rear door closure system - After discussion with Mahindra agreed to remove columns between grid M-N Points discussed with Mr. Dnyaneshwar S.
15.6 |  |  |  | Sumit B | TKAB | Rajeev P | 2025-08-21 | Hemming Bed document shared for verification |  | 2025-08-27 |  | 2025-08-22 | Close
16.8 |  |  |  | Sumit B | TKAB | Akhil N | 2025-08-21 | Sealer System technical specification shared for approval,Mahindra to confirm for futher ordering |  | 2025-08-26 |  |  | WIP | Ordering ;Approval for FFA15 & BSA30 LH RH Systems receieved from Mahindra on 9TH Sep. TKAB to review feasibilityfor Preform Sealant
18 |  |  |  | Vilas .V | TKAB | Rahul K | 2025-08-21 | UB Clamp queries shared, Mahindra to check & provide feedback |  | 2025-08-25 |  | 2025-09-08 | Close | UB required PLP coordinates Shared. Coordinates received from Mahindra on 8th Sep
19.2 |  |  |  | Vilas .V | TKAB | Mahantesh N | 2025-08-20 | Confirmation on Pnuematic Component list as per mail from Vilas |  | 2025-08-25 |  | 2025-08-28 | Close | Discuseed in meeting ,Confirmation awaited via email
20.4 |  |  |  | Vilas .V | TKAB | Dnyaneshwar G | 2025-08-20 | Destaco rework check for Misumi Pins. As per Destaco Pin cylinder cannot be reworked |  | 2025-08-25 |  | 2025-08-28 | Close | Destaco to provide cylinders with rework.
21.6 |  |  |  | Rohit . Z | TKAB | Mahantesh N | 2025-08-22 | Roof Line existing reference data required for simulation |  | 2025-08-22 |  | 2025-08-29 | Close
22.8 |  |  |  | Vilas .V | TKAB | Mahantesh N | 2025-08-21 | Manual line activities reference cycle time required | 2025-08-21 | 2025-08-25 |  | 2025-08-22 | Close | W610 reference to be used.
24 |  |  |  | Amol . G | Mahindra | Sumit | 2025-08-22 | tkAB to optimize SEW motors, drives for PRB. |  | 2025-09-12 |  | 2025-09-08 | Close
25.2 |  |  |  | Amol . G | Mahindra | Vilas | 2025-08-22 | Framer concept for CAB & Cargo |  | 2025-08-28 |  | 2025-09-10 | Close | Framer concept shared. Checked by Raghav & Rahul K. Tkab Proposed Z direction pnuematic working. Approval for Pneumatic working received from Mahinrda in meeting dated 10th Sep 25
26.4 |  |  |  | Amol . G | Mahindra | Vilas | 2025-08-22 | Cylinder to be used for inner & outer grippers. tkAB to check the same. |  | 2025-08-28 |  | 2025-08-29 | Close
27.6 |  |  |  | Amol . G | Mahindra | Rohit | 2025-08-22 | Payload of Cargo UB & MB to be freezed on priority. |  | 2025-09-04 |  | 2025-09-03 | Close | feedback provided on priority grippers as requested by Mahindra.
28.8 |  |  |  | Amol . G | Mahindra | Prathamesh | 2025-08-22 | Obara JB box to considered big size |  | Information |  | 2025-08-29 | Close | Need to consider big Size JB
30 |  |  |  | Amol . G | Mahindra | Sumit | 2025-08-22 | Tri party Meeting to organize between Tkab ,Tuenkers & SEW for PRB |  | 2025-09-24 |  | 2025-09-25 | Close | PRB POP UP Lifter Stroke fnalization in progress, Thenafter meeting will be organised
31.2 |  |  |  | Vias | TKAB | Mahantesh N | 2025-08-25 | Pneumatic component aapproval ,Need confirmation on destaco clamps & cylinders |  | 2025-08-30 | Mahindra to provide approval on series used as discussed in weekly review. | 2025-09-11 | Close | 82P35- For under body hook pin clamp , 86P & 86D for locating pin packages, 82M-4E- for Power clamps. Rest all approved.
32.4 |  |  |  | Harshal.B | TKAB | Prashant T | 2025-08-26 | Clarification on station where variant boxes need to be considered |  | 2025-08-28 |  | 2025-08-29 | Close | As per email shared by Prashant .T
33.6 |  |  |  | Harshal.B | TKAB | Prashant T | 2025-08-26 | Review of Robot Inside IO module and IO list details |  | 2025-08-28 |  | 2025-09-04 | Close | Will consider as per email shared by Prashant .T
34.8 |  |  |  | Rohit . Z | TKAB | Shubham S | 2025-08-29 | The M900iB-330L robot appears to be approximately 25% slower than the standard weld robot R2000iC-210F-should we consider the same timing |  | 2025-08-30 |  | 2025-09-04 | Close | As per mail from Shubham we are considering 25% slow time
36 |  |  |  | Rohit . Z | TKAB | Shubham S | 2025-08-29 | Confirmation regarding SSW ( 4 sec/spot timing for robots with payloads of 400 kg and above) has been validated by M&M -this robot tends to take longer for the weld operation plus movement to the next spot. |  | 2025-08-30 |  | 2025-09-04 | Close | To be considered as per mail from Shubham.
37.2 |  |  |  | Prashant T | TKAB | Vilas | 2025-08-29 | Meeting request for process review to be organize for CAB ,Cargo & closure |  | 2025-08-30 |  | 2025-09-03 | Close | Meeting started from 02-Sep,Cargo & Closure on Tue,Wed & thursday
38.4 |  |  |  | Rohit . Z | Tkab | Akhil /Shubham | 2025-09-01 | Fanuc motor details required for weld guns |  | 2025-09-03 |  | 2025-09-04 | Close
39.6 |  |  |  | Harshal.B | Tkab | Prashant T | 2025-09-02 | Required approval for Tower Lamp model |  | 2025-09-03 |  | 2025-09-04 | Close | TKAb will Proceed with the Scheme for the tower lamp shard by Prashant T .
40.8 |  |  |  | Vaibhav Chavan | Mahindra | Vilas | 2025-08-29 | Civil Utility with pit details |  | 2025-10-20 |  |  | WIP | Will be confirmed after concept DAP
42 |  |  |  | Rohit . Z | TKAB | Shubham S + Prashant T | 2025-09-05 | Dresspack designs required from Becker |  | 2025-09-09 |  |  | Close | Details recievd from Mahindra, TKAB checking the dresspack details, will share feedback. Controls details required for ATC finalization
43.2 |  |  |  | Rushikesh K | TKAB | Rushikesh W | 2025-09-09 | Closure process clarification of RD_Q004 issue |  | 2025-09-11 |  | 2025-09-15 | Close | Feedback received from M&M on 11th Sep, TKAB will be concluding after Concept review, Point discussed and closed with Mahindra
44.4 |  |  |  | Rushikesh K | TKAB | Shubham S | 2025-09-09 | Need feedback regarding UB cargo Cycle Time overshoot |  | 2025-09-11 |  |  | WIP | received revised CSV ,TKAb will work on new inputs tKAB provided feedbacks. Still issue in cycle time.
45.6 |  |  |  | Vikas P | TKAB | Dyaneshwar S | 2025-09-08 | Need feedback on Closure Line DFM |  | 2025-09-11 |  | 2025-09-24 | Close | Feedback received from M&M on 11th Sep, TKAB reviewing the feedback
46.8 |  |  |  | Harshal.B | TKAB | Prashant T | 2025-09-03 | Need to discuss & have approval on Following Points: 1.Conceptual Review of Electrical Power and Ethernet Scheme 2.Robot Architecture Discussed & need approval on same 3..Line Andon Electrical Scheme and Template Discussion |  | 2025-09-12 |  |  | WIP | 1.Conceptual Review of Electrical Power and Ethernet Scheme - Go ahaed given by M&M on 24th Sep 2.Robot Architecture reviewed on 11-Sep- M &M shared final remarks on 17th Sep and gave go ahead. 3.Andon Electrical Scheme and Template Discussion - Pending - M&M will close by 8th Oct
48 |  |  |  | Prathamesh T | TKAB | Prashant T | 2025-09-08 | Push button make to be confirmed, Schnider or Teknic for all control boxes & panel. |  | 2025-09-11 |  | 2025-09-11 | Close | Received go ahead from M&M for Teknic Make for all HMI/OP box/Gate Box.
49.2 |  |  |  | Harshal.B | TKAB | Prashant T | 2025-09-11 | Mahindra to provide PLC IO configuration or actual PLC unit image for roof line to update PLC I¦O's in drawing |  | Information |  |  | Close | For roof line PLC-A panel- Agreed M&M will provide PLC 1756-36/38ERMS during installation.
50.4 |  |  |  | Vikas P | TKAB | Dyaneshwar S | 2025-09-08 | Mahindra to share Comments on Query Sheet 008 mailed on 8th Sept for Closure Line |  | 2025-09-22 |  |  | WIP | Feedback received from M&M on 12th Sep, TKAB reviewing the feedback, will conclude after Concept Review
51.6 |  |  |  | Shripad R | TKAB | Prashant T | 2025-09-11 | Mahindra to confirm whether use of ISRA Vision or FANUC Based Vision System |  | 2025-09-15 |  |  | Open | Mahindra will close by 7th Oct
52.8 |  |  |  | Prashant T | Mahindra | Sumit B | 2025-09-11 | UB 05 liftr PRB proposal to be shared |  | 2025-09-30 |  |  | WIP | Quotes awaited from Tunkers
54 |  |  |  | Prashant T | TKAB | Vilas V | 2025-09-11 | Locking unit of PRB to be centre mounted |  | 2025-09-30 |  | 2025-09-30 | Close
55.2 |  |  |  | Shripad R | TKAB | Mahantesh N | 2025-09-17 | Mahindra to confirm RAL Code Schemes for Parts |  | 2025-09-24 |  |  | Open | Mahindra confirmed to provide feedback by 3-Oct
56.4 |  |  |  | Harshal.B | TKAB | Prashant T | 2025-09-17 | Mahindra has asked to change the design of Operator Box with new Concept and furthershare with Mahindra for Approval |  | 2025-09-24 |  | 2025-09-24 | Close | Prashant confirmed the design for Operator Box in a Meeting dated 24th Sep at TKAB Plant
57.6 |  |  |  | Vilas .V | TKAB | Prashant T | 2025-09-22 | Mahindra to confirm Peripheral Standards, If same to be followed as that of BEV - •Valve Bank Mounting Box •Light Curtain Mounting Stand •Cylinder Covers •HMI Stand •Run Bar Stand •Gripper Valve Bank Cover •Water Header Stand •Robot controller Stand. •SJB Stand |  | 2025-09-29 |  | 2025-10-03 | Close | Mahindra confirmed to follow BEV standards
58.8 |  |  |  | Sumit B | TKAB | Prashant T | 2025-09-24 | Mahindra to plan Tri party Meeting with SEW to planned for order finalising |  | 2025-09-25 |  | 2025-09-26 | Close | Mahindra gave go ahaed for odering of SEW after Tri Party Meeting with SEQ.
60 |  |  |  | Sumit B | TKAB | Prashant T | 25-05=25 | Dresspack Details and Control Connnectivity to Finalise ATC Ordering |  | 2025-09-30 |  |  | Close | TKAB needs Dresspack details and Contril Connectivity standards from Mahndra for ATC Finalization Mahindra to confirm the detaiils by 8th Oct
61.2 |  |  |  | Sumit B | TKAB | Mahantesh N | 2025-10-09 | Mahindra to provide a list where the Mylar chopping is not affected and unit 2D can be finalized by tkAB. Mahindra informed that TTO data for mylar chopping will be freezed by 15-Oct. |  | 2025-10-15 |  |  | Open
62.4
63.6
88

## M Z121 Schedule (hidden)
SIGNIFICANCE
MAKER - thyssenkrupp Automotive Body Solutions Private Limited |  |  |  | Project Start: | 2025-07-29 |  |  |  | PLAN |  |  |  |  | DELAY
PROJECT -Z121 |  |  |  | Today: | 2026-02-26 |  |  |  | ACTUAL |  |  |  |  | CURRENT
PM - SUMIT BABEL |  |  |  | Display Week: | 1 |  |  |  | 2025-07-29 | [6 empty] | 2025-08-05 | [6 empty] | 2025-08-12 | [6 empty] | 2025-08-19 | [6 empty] | 2025-08-26 | [6 empty] | 2025-09-02 | [6 empty] | 2025-09-09 | [6 empty] | 2025-09-16 | [6 empty] | 2025-09-23 | [6 empty] | 2025-09-30 | [6 empty] | 2025-10-07 | [6 empty] | 2025-10-14 | [6 empty] | 2025-10-21 | [6 empty] | 2025-10-28 | [6 empty] | 2025-11-04 | [6 empty] | 2025-11-11 | [6 empty] | 2025-11-18 | [6 empty] | 2025-11-25 | [6 empty] | 2025-12-02 | [6 empty] | 2025-12-09 | [6 empty] | 2025-12-16 | [6 empty] | 2025-12-23 | [6 empty] | 2025-12-30 | [6 empty] | 2026-01-06 | [6 empty] | 2026-01-13 | [6 empty] | 2026-01-20 | [6 empty] | 2026-01-27 | [6 empty] | 2026-02-03 | [6 empty] | 2026-02-10 | [6 empty] | 2026-02-17 | [6 empty] | 2026-02-24 | [6 empty] | 2026-03-03 | [6 empty] | 2026-03-10 | [6 empty] | 2026-03-17 | [6 empty] | 2026-03-24 | [6 empty] | 2026-03-31 | [6 empty] | 2026-04-07 | [6 empty] | 2026-04-14 | [6 empty] | 2026-04-21 | [6 empty] | 2026-04-28 | [6 empty] | 2026-05-05 | [6 empty] | 2026-05-12 | [6 empty] | 2026-05-19 | [6 empty] | 2026-05-26 | [6 empty] | 2026-06-02 | [6 empty] | 2026-06-09 | [6 empty] | 2026-06-16 | [6 empty] | 2026-06-23
[9 empty] | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21
Sr.No. |  | ACTIVITY | RESPONSIBLE | PROGRESS | START | END | ACTUAL VS PLAN | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Weld Line Design, DAP & 2D Release | 1.1 | PO /LOI | Mahindra | 100% | 2025-07-28 | 2025-08-04 | PLAN | DAYS: 8
|  |  |  | 100% | 2025-07-28 | 2025-09-03 | ACTUAL | DAYS: 38
| 1.2 | Project Kick-Off Meeting with Customer | Mahindra / tkAB | 100% | 2025-07-30 | 2025-07-30 | PLAN | bar: DAYS
|  |  |  | 100% | 2025-07-30 | 2025-07-30 | ACTUAL | bar: DAYS
| 1.3 | Product data & document sharing | Mahindra | 100% | 2025-07-31 | 2025-08-04 | PLAN | DAYS: 5
|  |  |  | 100% | 2025-08-04 | 2025-08-14 | ACTUAL | DAYS: 11
| 1.4 | Process Validation | tkAB | 100% | 2025-08-01 | 2025-08-26 | PLAN | DAYS: 26
|  |  |  | 90% | 2025-08-15 |  | ACTUAL
| 1.7 | Process Review | Mahindra / tkAB | 100% | 2025-08-26 | 2025-08-29 | PLAN | DAYS: 4
|  |  |  | 100% | 2025-09-15 | 2025-09-26 | ACTUAL | DAYS: 12
| 1.6 | Concept 3D design | tkAB | 100% | 2025-08-11 | 2025-09-10 | PLAN | DAYS: 31
|  |  |  | 100% | 2025-08-19 | 2025-09-14 | ACTUAL | DAYS: 27
| 1.7 | Concept Design Review with Mahindra | Mahindra / tkAB | 100% | 2025-09-08 | 2025-09-12 | PLAN | DAYS: 5
|  |  |  | 100% | 2025-09-15 | 2025-09-26 | ACTUAL | DAYS: 12
| 1.8 | Long Lead BOM preparation & approval from Mahindra | Mahindra / tkAB | 100% | 2025-08-11 | 2025-09-20 | PLAN | DAYS: 41
|  |  |  | 100% |  |  | ACTUAL
| 1.9 | PO for long lead items | tkAB | 100% | 2025-09-01 | 2025-10-30 | PLAN | DAYS: 60
|  |  |  | 90% | 2025-09-15 |  | ACTUAL
| 1.10 | 3D Design | tkAB | 100% | 2025-09-12 | 2025-10-10 | PLAN | DAYS: 29
|  |  |  | 90% | 2025-09-28 |  | ACTUAL
| 1.11 | FINAL _ DAP | Mahindra / tkAB | 100% | 2025-10-13 | 2025-10-17 | PLAN | DAYS: 5
|  |  |  | 100% | 2025-10-15 | 2025-11-08 | ACTUAL | DAYS: 25
| 1.12 | Design updation ,Detailing & Final Release | tkAB | 100% | 2025-10-20 | 2025-11-30 | PLAN | DAYS: 42
|  |  |  | 81% | 2025-10-30 |  | ACTUAL
| 1.13 | Electrical Design | tkAB | 100% | 2025-10-13 | 2025-11-27 | PLAN | DAYS: 46
|  |  |  | 95% | 2025-10-15 |  | ACTUAL
| 1.14 | Offline programming (PLC) | tkAB | 26% | 2025-11-24 | 2026-01-23 | PLAN | DAYS: 61
|  |  |  | 3% | 2025-12-22 |  | ACTUAL
| 1.15 | FINAL _ Electrical Design Review E -DAP & corrections | Mahindra / tkAB | 100% | 2025-12-01 | 2025-12-05 | PLAN | DAYS: 5
|  |  |  | 100% | 2025-12-08 | 2025-12-10 | ACTUAL | DAYS: 3
Simulation, OLP & VC | 2.1 | Robot simulation Concept | tkAB | 100% | 2025-09-15 | 2025-10-30 | PLAN | DAYS: 46
|  |  |  | 100% | 2025-09-30 |  | ACTUAL
| 2.2 | Detailed Simulation | tkAB | 100% | 2025-10-30 | 2025-11-14 | PLAN | DAYS: 16
|  |  |  | 80% | 2025-11-14 |  | ACTUAL
| 2.3 | FINAL _ Simulation Approval ( SAP ) | Mahindra / tkAB | 100% | 2025-11-15 | 2025-11-22 | PLAN | DAYS: 8
|  |  |  | 80% | 2025-11-14 |  | ACTUAL
| 2.4 | OLP Preparation | tkAB | 0% | 2025-11-23 | 2026-01-12 | PLAN | DAYS: 51
|  |  |  | 0% |  |  | ACTUAL
| 2.4 | OLP Submit | tkAB | 0% | 2026-01-10 | 2026-01-20 | PLAN | DAYS: 11
|  |  |  | 0% |  |  | ACTUAL
| 2.5 | FINAL _ OLP Approval ( OLP B/O ) | Mahindra / tkAB | 0% | 2026-01-20 | 2026-01-24 | PLAN | DAYS: 5
|  |  |  | 0% |  |  | ACTUAL
| 2.6 | Final PLC& HMI program submission | tkAB | 0% | 2026-01-25 | 2026-02-14 | PLAN | DAYS: 21
|  |  |  | 0% |  |  | ACTUAL
| 2.7 | IO mapped VC ready Simulation cells | tkAB | 0% | 2026-02-14 | 2026-03-01 | PLAN | DAYS: 16
|  |  |  | 0% |  |  | ACTUAL
| 2.8 | Virtual Commissioning testing & validation | tkAB | 0% | 2026-03-02 | 2026-03-17 | PLAN | DAYS: 16
|  |  |  | 0% |  |  | ACTUAL
| 2.8 | FINAL _ Virtual Commissioning Buy-off | Mahindra / tkAB | 0% | 2026-03-18 | 2026-04-02 | PLAN | DAYS: 16
|  |  |  | 0% |  |  | ACTUAL
Manufacturing, Assembly & Self certify | 3.1 | Manufacturing | tkAB | 35% | 2025-11-10 | 2026-01-09 | PLAN | DAYS: 61
|  |  |  | 35% | 2025-11-10 |  | ACTUAL
| 3.2 | Long lead BO items receipt | tkAB | 34% | 2025-11-20 | 2026-03-20 | PLAN | DAYS: 121
|  |  |  | 34% | 2025-11-20 |  | ACTUAL
| 3.12 | Mechanical & Electrical assembly of fixtures | tkAB | 3% | 2025-12-10 | 2026-01-15 | PLAN | DAYS: 37
|  |  |  | 0% | 2025-12-10 |  | ACTUAL
| 3.13 | CMM Inhouse, Gap Setting & Part fitment | tkAB | 0% | 2026-01-06 | 2026-02-06 | PLAN | DAYS: 32
|  |  |  | 0% |  |  | ACTUAL
| 3.14 | IO check & electrical check | tkAB | 0% | 2026-01-27 | 2026-02-13 | PLAN | DAYS: 18
|  |  |  | 0% |  |  | ACTUAL
| 3.15 | Supplier self certification - M1, M2, Controls, Process & Electrical HW | tkAB | 0% | 2026-02-10 | 2026-02-18 | PLAN | DAYS: 9
|  |  |  | 0% |  |  | ACTUAL
Limited Trial, Buy-off & Dispatch | 4.1 | M&M Sample Check - Process, M1 & M2 | Mahindra / tkAB | 0% | 2026-02-10 | 2026-02-19 | PLAN | DAYS: 10
|  |  |  | 0% |  |  | ACTUAL
| 4.2 | M&M Sample Check - Electrical HW & Controls | Mahindra / tkAB | 0% | 2026-02-17 | 2026-02-19 | PLAN | DAYS: 3
|  |  |  | 0% |  |  | ACTUAL
| 4.3 | Open points closing | tkAB | 0% | 2026-02-19 | 2026-02-22 | PLAN | DAYS: 4
|  |  |  | 0% |  |  | ACTUAL
| 4.4 | FINAL _ Buy-off | Mahindra / tkAB | 0% | 2026-02-19 | 2026-02-26 | PLAN | DAYS: 8
|  |  |  | 0% |  |  | ACTUAL
| 4.5 | Dismantling & Packing | tkAB | 0% | 2026-02-21 | 2026-03-05 | PLAN | DAYS: 13
|  |  |  | 0% |  |  | ACTUAL
| 4.6 | Shipping & Receipt @ Chakan | tkAB | 0% | 2026-02-22 | 2026-03-06 | PLAN | DAYS: 13
|  |  |  | 0% |  |  | ACTUAL
Onsite | 5 | Line Installation | tkAB | 0% | 2026-03-02 | 2026-04-21 | PLAN | DAYS: 51
|  |  |  | 0% |  |  | ACTUAL
| 6 | Commissioning & Trial Build | tkAB | 0% | 2026-03-22 | 2026-04-21 | PLAN | DAYS: 31
|  |  |  | 0% |  |  | ACTUAL
| 7 | TTO | Mahindra | 0% | 2026-04-22 | 2026-05-31 | PLAN | DAYS: 40
|  |  |  | 0% |  |  | ACTUAL
| 8 | Ready for VP Build | Mahindra / tkAB | 0% | 2026-06-01 |  | PLAN
|  |  |  | 0% |  |  | ACTUAL
Note on J6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.
Note on C7: Babel, Sumit: PO is yet to be received
Note on G14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data Received on 14-Aug ,Work Started on 15-Aug
Note on C19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Delayed By 1 Week

## Procurement Plan
PROCUREMENT PLAN MAHINDRA Z121
Sno | Item | Approval Details | Qty Required | Qty Pending | Qty Received | Make | Budget | Release required from |  | Expected Release from Design | Released Status | RFQ Release from PSM (Planned) | PO release to supplier (Planned) | Min. STD Lead time in Weeks | Delivery Date required @ tkAB (Planned) | Delivery date as per order acceptance | REMARKS
1 | ROCKWELL Drives for Conveyor (PRB) |  | 12 | 12 | 0 | AB | 43000000 | Prathamesh | Nilesh G | 2025-11-15 | Ordering Done | 2025-11-20 | 2025-11-25 | 8 | 2026-01-20 | 2026-01-20
2 | Safety Mats |  | 116 | 116 | 0 | AB | 8297016 | Vilas | Narayan M | 2025-11-13 | Ordering Under Finalization | 2025-11-18 | 2025-11-23 | 12 | 2026-02-15
3 | Rolling Shutter |  | 2 | 2 | 0 | Avians/Nivha | 540000 | Vilas | Suyog C | 2025-12-02 | Ordering Under Finalization | 2025-12-07 | 2025-12-12 | 10 | 2026-02-20
4 | PRB Sensors |  | 80 | 64 | 16 | BALLUFF | 616000 | Harshal | Narayan M | 2025-11-01 | Ordering Done | 2025-11-06 | 2025-11-11 | 10 | 2026-01-20 | 2026-01-15
5 | Tower Lamp/Status Lamp |  | 236 | 0 | 236 | Banner | 1688889 | Vinay | Narayan M | 2025-11-25 | Received | 2025-11-30 | 2025-12-05 | 8 | 2026-01-30 | 2026-01-20
6 | Variant Box |  | 70 | 70 | 0 | Banner | 901098 | Harshal | Narayan M | 2025-11-25 | Ordering Done | 2025-11-30 | 2025-12-05 | 8 | 2026-01-30 | 2026-01-23
7 | Dresspack Installation (Service scope Only) |  | 1 | 1 | 0 | Becker | 241481 | Prathamesh | Narayan M | 2025-11-23 | Ordering Done | 2025-11-28 | 2025-12-03 | 8 | 2026-01-28 | 2026-01-27
8 | ATC Cables |  | 156 | 156 | 0 | Becker | 450000 | Harshal | Narayan M | 2025-11-26 | Ordering Done | 2025-12-01 | 2025-12-06 | 8 | 2026-01-31 | 2026-01-31
9 | Guide Rollers |  | 150 | 0 | 150 | Blickle | 369930 | Vilas | Shekhar P | 2025-10-05 | Received | 2025-10-10 | 2025-10-15 | 8 | 2025-12-10 | 2025-12-10
10 | CKD Brake Cylinders |  | 31 | 31 | 0 | CKD | 2058407 | Vilas | Suyog C | 2025-11-11 | Ordering Done | 2025-11-16 | 2025-11-21 | 10 | 2026-01-30 | 2026-02-02
11 | Power Cylinders (Clamp/Guide./Compact) & Fittings |  | 2533 | 1606 | 927 | DESTACO | 29300000 | Vilas | Shekhar P | 2025-10-08 | Partially Recieved | 2025-10-13 | 2025-10-18 | 10 | 2025-12-27 | 2026-01-20
12 | PRB Rollers |  | 130 | 130 | 0 | Dugomrulli | 1530000 | Vilas | Shekhar P | 2025-11-04 | Ordering Done | 2025-11-09 | 2025-11-14 | 14 | 2026-02-20 | 2026-02-25
13 | Drive Shafts for framer |  | 8 | 0 | 8 | Elbe | 510192 | Vilas | Suyog C | 2025-09-15 | Received | 2025-09-20 | 2025-09-25 | 16 | 2026-01-15 | 2025-11-20
14 | Gate Switches |  | 52 | 0 | 52 | Euchner | 873600 | Prathamesh | Narayan M | 2025-09-30 | Received | 2025-10-05 | 2025-10-10 | 16 | 2026-01-30 | 2025-11-20
15 | EGT Profile |  | 6657 | 6657 | 0 | F EE | 364500 | Vilas | Suyog C | 2025-10-23 | Ordering Done | 2025-10-28 | 2025-11-02 | 12 | 2026-01-25 | 2026-01-20
16 | Vision for Pick and Place |  | 1 | 1 | 0 | FANUC | 3000000 | Vilas | Nilesh G | 2025-11-11 | Ordering Done | 2025-11-16 | 2025-11-21 | 10 | 2026-01-30 | 2026-03-25
17 | FESTO equipments |  | 189 | 59 | 130 | FESTO | 19000713 | Vilas | Narayan M | 2025-11-10 | Partially Recieved | 2025-11-15 | 2025-11-20 | 8 | 2026-01-15 | 2026-01-20
18 | Rulers For Framers |  | 20 | 0 | 20 | Ganter | 30000 | Vilas | Narayan M | 2025-09-02 | Received | 2025-09-07 | 2025-09-12 | 12 | 2025-12-05 | 2025-11-15
19 | PRB Timing Belts |  | 150 | 32 | 118 | Gates | 541000 | Vilas | Shekhar P | 2025-10-31 | Ordering Done | 2025-11-05 | 2025-11-10 | 8 | 2026-01-05 | 2025-12-30
20 | Utility |  | 1 | 1 | 0 | GI | 10000000 | Nitin Shinde | Suyog C | 2025-12-10 | Ordering Done | 2025-12-15 | 2025-12-20 | 6 | 2026-01-31 | 2026-01-15
21 | Turn Table with SEW Motor |  | 9 | 9 | 0 | Goizeper | 7907075.9085 | Vilas | Suyog C | 2025-11-02 | Ordering Done | 2025-11-07 | 2025-11-12 | 12 | 2026-02-04 | 2026-02-04
22 | Trunion with SEW Motor |  | 5 | 5 | 0 | Goizeper | 3924864.0915 | Vilas | Suyog C | 2025-11-02 | Ordering Done | 2025-11-07 | 2025-11-12 | 12 | 2026-02-04 | 2026-02-04
23 | Vin Punching |  | 2 | 0 | 2 | Gravotech | 1540000 | Vilas | Narayan M | 2025-12-09 | Received | 2025-12-14 | 2025-12-19 | 6 | 2026-01-30 | 2025-12-31
24 | Harting Connectors |  | 2320 | 0 | 2320 | Harting | 120000 | Harshal | Narayan M | 2025-10-19 | Received | 2025-10-24 | 2025-10-29 | 6 | 2025-12-10 | 2025-12-10
25 | Bellow Covers for framer |  | 16 | 0 | 16 | Hema | 95000 | Vilas | Suyog C | 2025-09-02 | Received | 2025-09-07 | 2025-09-12 | 12 | 2025-12-05 | 2025-11-30
26 | Control Panel Mounting Clips/Terminal Blocks |  | 4450 | 3410 | 1040 | IDEC | 1112500 | Prathamesh | Nilesh G | 2025-12-06 | Ordering Done | 2025-12-11 | 2025-12-16 | 8 | 2026-02-10 | 2026-02-12
27 | Drag Chains for framer |  | 2 | 0 | 2 | Igus | 96800 | Vilas | Narayan M | 2025-10-14 | Received | 2025-10-19 | 2025-10-24 | 6 | 2025-12-05 | 2025-10-25
28 | Lifter Mechanism for roof bow |  | 1 | 1 | 0 | Impression System | 1150000 | Vilas | Suyog C | 2025-12-06 | Ordering Done | 2025-12-11 | 2025-12-16 | 8 | 2026-02-10 | 2026-02-25
29 | Bearings for Framer |  | 139 | 0 | 139 | INA / FAG | 115927 | Vilas | Narayan M | 2025-09-02 | Received | 2025-09-07 | 2025-09-12 | 12 | 2025-12-05 | 2025-11-15
30 | Vision for Robotic Sealant System |  | 4 | 4 | 0 | KEYENCE | 3114480 | Vilas | Narayan M | 2025-12-09 | Ordering Done | 2025-12-14 | 2025-12-19 | 6 | 2026-01-30 | 2026-01-30
31 | Light Curtains |  | 121 | 121 | 0 | KEYENCE | 4447300 | Vilas | Narayan M | 2025-12-16 | Ordering Done | 2025-12-21 | 2025-12-26 | 5 | 2026-01-30 | 2026-01-30
32 | Panel Wiring Cables |  | 100 | 0 | 100 | Lapp | 3100000 | Prathamesh | Narayan M | 2025-11-05 | Ordering Done | 2025-11-10 | 2025-11-15 | 8 | 2026-01-10 | 2026-01-31
33 | Field Wiring Cables |  | 20040 | 10240 | 9800 | Lapp | 4921611 | Vinay | Narayan M | 2025-10-22 | Ordering Done | 2025-10-27 | 2025-11-01 | 10 | 2026-01-10 | 2026-01-31
34 | Field Cable Trays |  | 1 | 1 | 0 | LOCAL | 8162419.4733 | Vinay | Suyog C | 2025-11-24 | Ordering Done | 2025-11-29 | 2025-12-04 | 6 | 2026-01-15 | 2026-01-15
35 | Robot Pedestals |  | 69 | 6 | 63 | LOCAL | 5175000 | Vilas | Rahul.S | 2025-11-14 | Partially Recieved | 2025-11-19 | 2025-11-24 | 6 | 2026-01-05 | 2026-01-05
36 | Weld Timer Stands |  | 62 | 62 | 0 | LOCAL | 280000 | Vilas | Shekhar P | 2025-12-23 | Ordering Done | 2025-12-28 | 2026-01-02 | 4 | 2026-01-30 | 2026-01-30
37 | Adaptor Plate |  | 9 | 9 | 0 | Local | 1131000 | Vilas | Suyog C | 2025-12-16 | Ordering Done | 2025-12-21 | 2025-12-26 | 5 | 2026-01-30
38 | Castor Wheels |  | 10 | 10 | 0 | Local | 30000 | Vilas | Suyog C | 2025-11-24 | Ordering Done | 2025-11-29 | 2025-12-04 | 6 | 2026-01-15
39 | Robot controller plate BOM |  | 62 | 62 | 0 | Manufacturing | 31000 | Harshal | Shekhar P | 2025-11-10 | RFQ Released | 2025-11-15 | 2025-11-20 | 8 | 2026-01-15
40 | APC Hanger |  | 33 | 0 | 33 | Manufacturing | 450000 | Vilas | Shekhar P | 2026-01-15 | Under Design | 2026-01-20 | 2026-01-25 | 7 | 2026-03-15
41 | Hemming Beds |  | 6 | 6 | 0 | Manufacturing | 3900000 | Vilas | Shekhar P | 2025-11-06 | FD, RD, TG Casting Ready | 2025-11-11 | 2025-11-16 | 10 | 2026-01-25
42 | In process trollies |  | 47 | 47 | 0 | Manufacturing | 1125000 | Vilas | Rahul.S | 2026-01-08 | Ordering Under Finalization | 2026-01-13 | 2026-01-18 | 8 | 2026-03-15
43 | Tackles |  | 48 | 48 | 0 | Manufacturing | 350000 | Vilas | Rahul.S | 2026-01-22 | Ordering Under Finalization | 2026-01-27 | 2026-02-01 | 6 | 2026-03-15
44 | FRP Templates |  | 44 | 44 | 0 | Manufacturing | 150000 | Vilas | Shekhar P | 2025-12-09 | Ordering Done | 2025-12-14 | 2025-12-19 | 6 | 2026-01-30
45 | Strip Brushes for framer |  | 16 | 0 | 16 | Mink Bürsten | 22896 | Vilas | Suyog C | 2025-09-15 | Received | 2025-09-20 | 2025-09-25 | 16 | 2026-01-15 | 2025-11-20
46 | Pins and Profiles |  | 428 | 428 | 0 | MISUMI | 800000 | Vilas | Narayan M | 2025-11-09 | Ordering Done | 2025-11-14 | 2025-11-19 | 6 | 2025-12-31 | 2025-12-31
47 | Ethernet Cables / Sensor Cables/Connection Cables |  | 2051 | 1758 | 293 | MURR | 17690405 | Prathamesh | Narayan M | 2025-11-25 | Partially Recieved | 2025-11-30 | 2025-12-05 | 8 | 2026-01-30 | 2026-01-31
48 | Weld Guns |  | 6 | 0 | 6 | NASH | 3150000 | Rohit | Suyog C | 2025-09-25 | Ordering Done | 2025-09-30 | 2025-10-05 | 16 | 2026-01-25 | 2026-01-25
49 | Bushes for framer |  | 19 | 0 | 19 | Norelem | 25000 | Vilas | Narayan M | 2025-09-28 | Received | 2025-10-03 | 2025-10-08 | 12 | 2025-12-31 | 2025-12-31
50 | WATER SAVER / Weld Guns / Tip Dresser with stands |  | 8 | 8 | 0 | OBARA | 31608655 | Vilas / Rohit | Suyog C | 2025-10-29 | Ordering Done | 2025-11-03 | 2025-11-08 | 12 | 2026-01-31 | 2026-01-31
51 | Proxi Sensors |  | 1030 | 186 | 844 | Omron | 3166920 | Vilas | Narayan M | 2025-11-20 | Partially Recieved | 2025-11-25 | 2025-11-30 | 8 | 2026-01-25 | 2026-02-08
52 | Limit Switches |  | 72 | 72 | 0 | Omron | 150000 | Vilas | Narayan M | 2025-10-23 | Ordering Done | 2025-10-28 | 2025-11-02 | 12 | 2026-01-25 | 2026-01-21
53 | Robotic Sealant System |  | 3 | 3 | 0 | PATVIN | 17550000 | Vilas | Suyog C | 2025-09-08 | Ready For Dispatch | 2025-09-13 | 2025-09-18 | 16 | 2026-01-08 | 2026-01-08
54 | Lubrication Fittings for framer |  | 56 | 0 | 56 | PERMA-TEC | 157140 | Vilas | Suyog C | 2025-09-15 | Received | 2025-09-20 | 2025-09-25 | 16 | 2026-01-15 | 2025-11-20
55 | Suction Cup ,Holder & Vaccum Generator |  | 426 | 325 | 101 | PIAB | 1900000 | Vilas | Narayan M | 2025-11-24 | Ordering Done | 2025-11-29 | 2025-12-04 | 6 | 2026-01-15 | 2026-01-21
56 | Couplings for framer |  | 37 | 25 | 12 | Ringspann | 135000 | Vilas | Shekhar P | 2025-09-27 | Partially Recieved | 2025-10-02 | 2025-10-07 | 12 | 2025-12-30 | 2026-01-06
57 | HMI with stand |  | 69 | 69 | 0 | ROCKWELL | 3800000 | Prathamesh | Narayan M | 2025-09-30 | Ordering Done | 2025-10-05 | 2025-10-10 | 16 | 2026-01-30 | 2026-01-15
58 | Oilless Bushes |  | 1160 | 1160 | 0 | Sankyo | 580000 | Vilas | Narayan M | 2025-11-09 | Ordering Done | 2025-11-14 | 2025-11-19 | 6 | 2025-12-31 | 2025-12-31
59 | Bearings for framer plummer block |  | 14 | 0 | 14 | Schaeffler | 75300 | Vilas | Narayan M | 2025-09-02 | Received | 2025-09-07 | 2025-09-12 | 12 | 2025-12-05 | 2025-11-15
60 | Biometric SW Cable |  | 72 | 72 | 0 | SCHNEIDER | 200000 | Prathamesh | Narayan M | 2025-12-21 | Ordering Done | 2025-12-26 | 2025-12-31 | 6 | 2026-02-11 | 2026-02-11
61 | SEW Drives / Motor / Cable |  | 30 | 3 | 27 | SEW | 22284538.8656 | Prathamesh | Suyog C | 2025-10-04 | Partially Recieved | 2025-10-09 | 2025-10-14 | 14 | 2026-01-20 | 2026-01-16
62 | Disconect Switch/MCB/Spreader Links |  | 4576 | 1463 | 3113 | Siemens | 3098755 | Harshal | Narayan M | 2025-10-18 | Partially Recieved | 2025-10-23 | 2025-10-28 | 12 | 2026-01-20 | 2026-01-20
63 | WATER HEADER |  | 52 | 20 | 32 | SMC | 954000 | Vilas | Narayan M | 2025-11-27 | Partially Recieved | 2025-12-02 | 2025-12-07 | 10 | 2026-02-15 | 2026-02-13
64 | Roller bed without lifter |  | 9 | 9 | 0 | tkAB | 5040000 | Vilas | Shekhar P | 2025-09-15 | Ordering Done | 2025-09-20 | 2025-09-25 | 16 | 2026-01-15 | 2026-01-15
65 | Control Panel |  | 8 | 8 | 0 | tkab | 27000000 | Prathamesh | Nilesh G | 2025-10-09 | Ordering Done | 2025-10-14 | 2025-10-19 | 14 | 2026-01-25 | 2026-01-25
66 | Fences |  | 1 | 1 | 0 | TROAX / INHOUSE | 8200000 | Vilas | Nilesh G | 2025-11-18 | Ordering Done | 2025-11-23 | 2025-11-28 | 12 | 2026-02-20 | 2026-02-20
67 | Robotic Stud |  | 1 | 0 | 1 | Tucker | 7727415 | Rohit | Suyog C | 2025-09-30 | Received | 2025-10-05 | 2025-10-10 | 16 | 2026-01-30 | 2025-12-31
68 | Pop Up Lifter |  | 8 | 8 | 0 | TUNKERS | 12731040 | Vilas | Nilesh G | 2025-10-21 | Ordering Done | 2025-10-26 | 2025-10-31 | 16 | 2026-02-20 | 2026-02-20
69 | APC Conveyour |  | 4 | 4 | 0 | TUNKERS | 9200000 | Vilas | Suyog C | 2025-10-14 | Ordering Done | 2025-10-19 | 2025-10-24 | 14 | 2026-01-30 | Awaited
70 | IO Modules |  | 73 | 0 | 73 | Turk | 1144932 | Prathamesh | Narayan M | 2025-09-30 | Ordering Done | 2025-10-05 | 2025-10-10 | 8 | 2025-12-05 | 2025-11-26
71 | Andon Display |  | 13 | 13 | 0 | Vertaxis | 325000 | Prathamesh | Narayan M | 2025-11-25 | Ordering Done | 2025-11-30 | 2025-12-05 | 8 | 2026-01-30 | 2026-02-05
72 | ATC Robot side |  | 41 | 41 | 0 | WALTHER | 19685646.8182 | Rohit | Suyog C | 2025-10-14 | Ordering Done | 2025-10-19 | 2025-10-24 | 14 | 2026-01-30 | 2026-02-20
73 | ATC Tool side |  | 91 | 91 | 0 | WALTHER | 43692533.1818 | Rohit | Suyog C | 2025-10-14 | Ordering Done | 2025-10-19 | 2025-10-24 | 14 | 2026-01-30 | 2026-02-20
74 | ATC Parking Stands |  | 91 | 91 | 0 | WALTHER | 3640000 | Vilas | Suyog C | 2025-10-14 | Ordering Done | 2025-10-19 | 2025-10-24 | 14 | 2026-01-30 | 2026-02-20
75 | Shock absorber for Framer |  | 155 | 129 | 26 | Weforma | 1020000 | Vilas | Narayan M | 2025-11-08 | Ordering Done | 2025-11-13 | 2025-11-18 | 6 | 2025-12-30 | 2025-12-30
76 | Roller Bearings, Rack, Pinion, Rails framer |  | 20 | 20 | 0 | WINKEL | 1646784 | Vilas | Suyog C | 2025-10-09 | In Transit | 2025-10-14 | 2025-10-19 | 14 | 2026-01-25 | 2026-01-23
77 | Water Hoses |  | 2200 | 2200 | 0 | Yasung | 777600 | Prathamesh | Narayan M | 2025-11-25 | Ordering Done | 2025-11-30 | 2025-12-05 | 8 | 2026-01-30 | 2026-01-20
Formulas:
Expected Release from Design = [RFQ Release from PSM (Planned)]-5
RFQ Release from PSM (Planned) = [PO release to supplier (Planned)]-5
PO release to supplier (Planned) = +[Delivery Date required @ tkAB (Planned)]-([Min. STD Lead time in Weeks]*7)
Note on Q36: Author: required for panel built
Note on Q37: Author: required for panel built